## Summary
FinOps SaaS — Feature Build Status
Source: IMPLEMENTATION_STATUS_MATRIX.md reconciled with lumen.html (commit f4795a4, May 24, 2026). Update Status on Feature Tracker sheet; this page recalculates.
Category | Built | Partial | In Progress | Not Built | Total | % Complete
Dashboards & Visualization | 9 | 0 | 0 | 2 | 11 | 81.82%
Cost Aggregation (Backend) | 8 | 0 | 0 | 0 | 8 | 100%
Cost Normalization | 3 | 0 | 0 | 0 | 3 | 100%
Credential Management | 8 | 0 | 0 | 1 | 9 | 88.89%
Budgeting & Cost Control | 3 | 2 | 0 | 1 | 6 | 66.67%
Optimization & Recommendations | 2 | 3 | 0 | 1 | 6 | 58.33%
Security & Access Control | 5 | 0 | 0 | 3 | 8 | 62.5%
User Management | 2 | 1 | 0 | 2 | 5 | 50%
APIs & Integrations | 1 | 0 | 0 | 6 | 7 | 14.29%
Advanced Analytics | 0 | 1 | 0 | 2 | 3 | 16.67%
Settings | 0 | 0 | 0 | 2 | 2 | 0%
TOTAL | 41 | 7 | 0 | 20 | 68 | 65.44%
Recommended next steps (per roadmap):
Phase 10: Azure + GCP credential UIs (26 pts, ~2 wks)
Phase 12: RBAC framework, backend user mgmt, audit logging (68 pts, ~3 wks)
Phase 13: Budget management + alerts (34 pts, ~2.5 wks)
Phase 14: Recommendation integration + cost impact tracking (34 pts)

## Feature Tracker
Category | Feature | Sub-Feature / Detail | Cloud Scope | Status | Phase | Story Points | Notes
Dashboards & Visualization | Executive Summary | C-level view, forecasts, strategic insights | Multi-cloud | Built | Done |  | In lumen.html
Dashboards & Visualization | Finance Portal | 90-day trends, cost drivers, account breakdown | Multi-cloud | Built | Done |  | In lumen.html
Dashboards & Visualization | FinOps Analytics | Service breakdown, AI services, recommendations | Multi-cloud | Built | Done |  | In lumen.html
Dashboards & Visualization | Team Cost Dashboard | Cost allocation, budgets, team resources | Multi-cloud | Built | Done |  | In lumen.html
Dashboards & Visualization | AWS Dashboard | AWS metrics, RI/SP, account hierarchy | AWS | Built | 11 | 13 | Added May 24, 2026 (commit f4795a4)
Dashboards & Visualization | Azure Dashboard | Azure metrics, reservations, subscriptions | Azure | Built | 11 | 13 | Added May 24, 2026
Dashboards & Visualization | GCP Dashboard | GCP metrics, CUD, projects | GCP | Built | 11 | 13 | Added May 24, 2026
Dashboards & Visualization | FOCUS Normalized View | Unified cross-cloud view using FOCUS fields | Multi-cloud | Built | 11 | 21 | Added May 24, 2026
Dashboards & Visualization | AI Cost Dashboard | Model costs, token analytics, optimization | Multi-cloud | Built | 11 | 21 | In lumen.html
Dashboards & Visualization | Custom Dashboard Builder | Drag-and-drop dashboard creation | Multi-cloud | Not Built | 16
Dashboards & Visualization | Scheduled Reports | Report generation and distribution | Multi-cloud | Not Built | 16
Cost Aggregation (Backend) | Cost Ingestion Engine | AWS CUR via S3 | AWS | Built | Done |  | Complete backend
Cost Aggregation (Backend) | Cost Ingestion Engine | Azure Cost Management API | Azure | Built | Done
Cost Aggregation (Backend) | Cost Ingestion Engine | GCP BigQuery billing export | GCP | Built | Done
Cost Aggregation (Backend) | Cost Schema Mapping | Provider schema -> internal schema | All | Built | Done
Cost Aggregation (Backend) | Service Categorization | 25+ AWS, 25+ Azure, 30+ GCP services | All | Built | Done
Cost Aggregation (Backend) | Multi-Tenant Isolation | Tenant separation in ingestion | All | Built | Done
Cost Aggregation (Backend) | Job Scheduling | cost_ingest, focus_transform jobs | All | Built | Done
Cost Aggregation (Backend) | Data Pipeline Monitoring | Job status tracking | All | Built | Done
Cost Normalization | FOCUS Schema Transformation | invoice_issuer, service_name, service_category | All | Built | Done
Cost Normalization | AI Service Classification | Claude, GPT-4, Vertex AI, etc. | All | Built | Done
Cost Normalization | Multi-Cloud Comparison | Cross-cloud analysis via FOCUS dashboard | All | Built | 11 |  | Unblocked by FOCUS dashboard (May 24)
Credential Management | AWS Credential UI | Create/edit/delete S3 config, test connection | AWS | Built | Done
Credential Management | Azure Credential UI | Service Principal auth, Cost API connection | Azure | Built | 10 | 13 | Built Jul 9, 2026 — unified CredentialManager.jsx with setup guides; wired to /api/v1 endpoints
Credential Management | GCP Credential UI | Service Account auth, BigQuery connection | GCP | Built | 10 | 13 | Built Jul 9, 2026 — unified CredentialManager.jsx with setup guides; wired to /api/v1 endpoints
Credential Management | Multi-Cloud Admin Hub | Unified credential view, provider status, sync metrics | All | Built | 10 | 21 | Added May 24, 2026
Credential Management | Config Validation (backend) | All three clouds | All | Built | Done
Credential Management | Test Connection (backend) | All three clouds | All | Built | Done
Credential Management | Credential Encryption | DB-level encryption | All | Built | Done
Credential Management | Credential Rotation | Automated key rotation | All | Not Built | 13
Credential Management | Multi-Config Support | Multiple configs per provider | All | Built | Done
Budgeting & Cost Control | Budget Tracking | Basic tracking in Team Dashboard | Multi-cloud | Built | 13 |  | Built Jul 11, 2026 — live actuals from FocusCost, utilization %, Live view in Budgets screen
Budgeting & Cost Control | Budget Creation | Hierarchical budget builder | Multi-cloud | Built | 13 | 21 | Built Jul 11, 2026 — /api/budgets CRUD, scoped by provider/category/account, RBAC-guarded
Budgeting & Cost Control | Budget vs Actual | Variance tracking | Multi-cloud | Built | 13 |  | Built Jul 11, 2026 — per-period + monthly history endpoint
Budgeting & Cost Control | Forecasting | Spend forecasting | Multi-cloud | Partial | 16 |  | Run-rate EOP forecast per budget built Jul 11; ML models pending
Budgeting & Cost Control | Alerts & Notifications | Threshold alerts | Multi-cloud | Partial | 13 | 13 | Threshold alerts (warning/over) in API+UI built Jul 11; email/Slack delivery pending
Budgeting & Cost Control | Budget Enforcement | Hard limits / actions | Multi-cloud | Not Built | 13
Optimization & Recommendations | Cost Optimization Recommendations | Static examples in FinOps Analytics | Multi-cloud | Built | 14 |  | Built Jul 11, 2026 — cost_recommendations.py: 3 detectors over FOCUS data, verified $4.6k/mo findings
Optimization & Recommendations | CSP-Native Recommendations | Trusted Advisor, Azure Advisor, GCP Recommender | All | Partial | 14 | 21 | Rule-based equivalents (SP/RI/CUD coverage, rightsizing, unused commitments) built Jul 11; direct Advisor API pulls pending
Optimization & Recommendations | Recommendation Tracking | Status workflow for recs | Multi-cloud | Built | 14 |  | Built Jul 11, 2026 — findings workflow (new→approved verified), dedupe on re-evaluation
Optimization & Recommendations | Cost Impact / ROI Calculation | Savings measurement | Multi-cloud | Partial | 14 | 13 | Estimated savings + confidence bands per finding built Jul 11; realized-impact via outcomes not yet exercised
Optimization & Recommendations | Backtest Framework | Optimization testing | Multi-cloud | Partial | 14 |  | Endpoint exists; logic is placeholder pending real signal data
Optimization & Recommendations | Automated Remediation | Auto-apply recommendations | Multi-cloud | Not Built | 17+
Security & Access Control | Multi-Tenant Isolation | Enforced at DB level | All | Built | Done
Security & Access Control | Tenant-Scoped Filtering | All queries filtered by tenant_id | All | Built | Done
Security & Access Control | Secrets Management | Credential encryption | All | Built | Done
Security & Access Control | RBAC Framework | Roles, hierarchy, permission enforcement | All | Built | 12 | 34 | Built Jul 10, 2026 — rbac.py: 6 roles, permission matrix, require_permission; enforced on credential routes
Security & Access Control | Row-Level Security | Scope by department/project | All | Not Built | 12
Security & Access Control | SSO / OAuth 2.0 | Okta, Auth0, Cognito | All | Not Built | 15
Security & Access Control | MFA Support | Multi-factor auth | All | Not Built | 15
Security & Access Control | Audit Logging | Audit log + viewer | All | Built | 12 | 21 | Built Jul 10, 2026 — AuditEvent writes on user/credential actions, /api/audit endpoint + UI trail
User Management | User Management UI | Provisioning, role & scope assignment screens | All | Built | 12 | 13 | UI added May 24; backend enforcement pending
User Management | User Provisioning (backend) | Create/manage users | All | Built | 12 |  | Built Jul 10, 2026 — /api/users CRUD, admin-only, self-lockout guards
User Management | Role & Scope Assignment (backend) | Department, project, account scopes | All | Partial | 12 |  | Role assignment Built Jul 10, 2026; dept/project scope assignment (row-level security) still pending
User Management | User Activity Tracking | Usage analytics | All | Not Built | 16
User Management | Delegation / Impersonation | Admin impersonation | All | Not Built | 17+
APIs & Integrations | REST API for Costs | 6 endpoints (summary, daily, by service...) | All | Built | Done
APIs & Integrations | GraphQL API | Flexible querying | All | Not Built | 15
APIs & Integrations | Webhook Support | Event notifications | All | Not Built | 15
APIs & Integrations | Slack Integration | Alerts and digests | All | Not Built | 15
APIs & Integrations | Email Reporting | Scheduled email reports | All | Not Built | 15
APIs & Integrations | BI Tool Integration | Tableau, PowerBI, Looker | All | Not Built | 15
APIs & Integrations | DataDog / NewRelic Integration | Observability cost correlation | All | Not Built | 17+
Advanced Analytics | Forecasting Models | ML-based spend forecasting | All | Not Built | 16
Advanced Analytics | Anomaly Detection | Spend anomaly alerts | All | Partial | 16 |  | UI prototype (anomalies.jsx in UI_src); no backend
Advanced Analytics | Custom Report Builder | Ad hoc reporting | All | Not Built | 16
Settings | Organization Settings | Org-level config | All | Not Built | 13
Settings | Notification Preferences | Per-user notification config | All | Not Built | 13